## Product Backlog
Vision |  | Stock control system that will capture customer orders and update relevant stock items
EPICS/Themes | User story No. | User Stories : As a < type of user >, I want < some goal > so that < some reason > | Priority | Estimates (story points) | Sprint Iteration | Tasks
Login/Registration/Nav | 1 | As any user of the stock control system I want to be able to navigate to customer, supplier, stock or orders screen to carry out my daily work tasks. | 1 | 1 | Sprint 1 | home screen with buttons to 4 other screens
Customer component | 4 | As a sales person I need to be able to create a customer record so that I can maintain my customer details. | 2 | 2 | Sprint 1 | Create an array to hold customer records. customerNo, name, address, telephone, gender and industry
Stock component | 11 | As an administrator I need to be able to add products to the system so that we can maintain product records | 3 | 3 | Sprint 1 | Create an array to hold products. productID , name, Description, price, quantity.
Supplier component | 8 | As an administrator I need to be able to add suppliers to the system so that we can maintain supplier records | 4 | 3 | Sprint 1 | Create an array to hold supliers. supplierNo, name, address, telephone, productSupplied
Orders component | 15 | As a sales person I need to be able to order multiple products for a customer order so that I can place orders for customers of items that are currently in stock. | 5 | 5 | Sprint 1 | Drop down box displaying products. Select the product and quantity required.
Stock component | 14 | As an administrator I need to be alerted when stock runs below 5 on any stock item so that I can reorder stock. | 6 | 2 | Sprint 1 | If statement to check wether quantity of any given item is below 5. A method in product class to do the check
Orders component | 16 | As a sales person I need to be view the total cost of a customer order so that I can see money due. | 7 | 3 | Sprint 2 | A drop down box of all customers in the system can be displayed and a customer then selected. The total cost is calculated by price*quantity. A method to calculate and display it if a button is clicked
Customer component | 5 | As a sales person I need to be able to select a customer record to update so that I can maintain my customer details. | 8 | 3 | Sprint 2 | A drop down box of all the customers to be displayed then when selected. An update method will be called and will give access to setter methods
Supplier component | 9 | As an administrator I need to be able to select a supplier record and update it so that I can maintain supplier records | 9 | 3 | Sprint 2 | A drop down box of all the suppliers to be displayed then when selected. An update method will be called and will give access to setter methods
Stock component | 12 | As an administrator I need to be able to update products to the system so that we can maintain product records | 10 | 3 | Sprint 2 | A drop down box of all the products to be displayed then when selected. An update method will be called and will give access to setter methods
Orders component | 17 | As a sales manager I can update the status of an order to maintain the order tracking. | 11 | 1 | Sprint 2 | A drop down box of all orders that can be selected, order status can be updated to pending, awaiting payment, fulfilled
Customer component | 6 | As a sales manager I need to be able to run customer reports so that I can view total sales by industry, area and sales person to monitor our sales. | 12 | 5 | Sprint 2
Login/Registration/Nav | 2 | As an administrator I need to be able to register user profiles so that a user can log into the system. | 13 | 5 | Sprint 3
Login/Registration/Nav | 3 | As any user of the system I need to be able to login to the system so that I can securely access the system | 14 | 2 | Sprint 3 | Provide users with login details. When a user attempts to log in the system user array list should be searched to ensure login details are correct
Customer component | 7 | As an administrator I need to be able to delete customer records so that I can maintain the system. | 15 | 2 | Sprint 3 | Drop down box of customer record. When a record is selected a button to delete it will be displayed
Supplier component | 10 | As an administrator I need to be able to delete suppliers to the system so that we can maintain supplier records | 16 | 2 | Sprint 3 | Drop down box of supplier records. When a record is selected a button to delete it will be displayed
Stock component | 13 | As an administrator I need to be able to delete products to the system so that we can maintain product records | 17 | 2 | Sprint 3 | Drop down box of products. When a record is selected a button to delete it will be displayed
|  | Team Capacity | 18 hours
|  | Total Points |  | 47

## Sprint 1 Backlog
User Story No. | Story Points | Task No. | Task Detail | Owner | Status | Hours remaining | Actual Time taken
1 | 1 | 1 | home screen with buttons to 4 other screens and 3 pictures of the team. The 4 buttons should bring you to the customer page, suppliers page, stock page, and orders page. | Victor | in progress
4 | 2 | 2 | Create an array to hold customer records. customerNo, name, address, telephone, gender and industry. Each variable will need a textfield to take in the details of the customer. |  | to do
11 | 3 | 3 | Create an array to hold products. productID , name, Description, price, quantity. Each variable will need a textfield to intake the products detail. |  | to do
8 | 3 | 4 | Create an array to hold supliers. supplierNo, name, address, telephone, productSupplied. Each variable will need a textfield to intake the supplier details |  | to do
15 | 5 | 5 | In the stock page there should be a drop down menu displaying the products. To add products the product should be selected and quantity required input throught a textfield. The stock amount of that product will than be updated |  | to do
14 | 2 | 6 | If statement to check wether quantity of any given item is below 5. A method in product class to do the check |  | to do

## Sprint 2 Backlog
User Story No. | Story Points | Task No. | Task Detail | Owner | Status | Hours remaining | Actual Time taken
16 | 3 | 7 |  |  | to do
5 | 3 | 8 |  |  | to do
9 | 3 | 9 |  |  | to do
12 | 3 | 10 |  |  | to do
17 | 1 | 11 |  |  | to do
6 | 5 | 12 |  |  | to do

## Sprint 3 Backlog
User Story No. | Story Points | Task No. | Task detail | Owner | Status | Hours remaining | Actual Time taken
2 | 5 | 13 |  |  | to do
3 | 2 | 14 |  |  | to do
7 | 2 | 15 |  |  | to do
10 | 2 | 16 |  |  | to do
13 | 2 | 17 |  |  | to do

## Sheet2
0 | Sprint 1 | To do
1 | Sprint 2 | In progress
2 | Sprint 3 | Done
3
5
8
13