## Product Backlog
Vision |  | Stock control system that will capture customer orders and update relevant stock items
EPICS/Themes | User story No. | User Stories : As a < type of user >, I want < some goal > so that < some reason > | Priority | Estimates (story points) | Sprint Iteration | Tasks
Stock Control |  | As a user I need to be able to navigate the main stock control page so that I can switch between adding items and viewing items | 1 | 1 | Sprint 1 | home screen with 2 buttons to 2 other screens
Stock Control |  | As a user I need to be able to add items to an items list so that I can add new items | 2 | 2 | Sprint 1 | Create an ArrayList to hold items. Items Object (itemName, expirationDate,itemType (luxury,essential,gift). Textfields should be displayed to take in the item details and and add button to add the the item to the items arrayList. When the add button is clicked a check should be made so that all fields are filled because all fields are mandatory. a unique ID should be generated for each item added to the array list.
Stock Control |  | As a user I need to be able to be to keep track of the number of a certain types of items | 3 | 3 | Sprint 1 | a method that counts the number of certain types of items in the array of items
Stock Control |  | As a user I need to be able to view all items so that I can check the expiration date and whats in stock | 4 | 3 | Sprint 1 | When the view items button is click a drop down list of the items in stock is displayed displaying also their expiration date
Stock Control |  | As a user I need to be able to select an item so that I can delete it if desired | 5 | 5 | Sprint 1 | When the drop down list is displayed the items must be selectable. Once selected a delete button can be clicked and if clicked the item selected will be removed from the the items list. A button to return to the main page must be included
Shopping basket and calculations |  | As a customer I need a drop down option so that I can select a desired itme type i.e luxury, essential and gift. | 6 | 2 | Sprint 1 | A drop down menu in a customer page will be displayed with all the types of items displayed which are selectable. Once selected the items of the type selected will be displayed.
Shopping basket and calculations |  | As a customer I need to know how much the types of items are so that I know how expensive they are . | 7 | 3 | Sprint 2 | When the types of items are displayed the price assosciated with that item should be displayed (Luxury £ 50, Essential £30, Gift £20)
Shopping basket and calculations |  | As a customer I want to know how much VAT is on each type of item so that I know the total cost | 8 | 3 | Sprint 2 | A method that will calculate the VAT of each of the item types is needed (Luxury @20%, Essential @10%, Gift @5%
Shopping basket and calculations |  | As customer I want to be able select the quantity of products so that I can fulfill my order | 9 | 3 | Sprint 2 | A textbox will take in the desired quantity of the item.
Shopping basket and calculations |  | As a customer I want to be able to calculate the total cost of my order so that I know the total cost | 10 | 3 | Sprint 2 | After calculating and adding the VAT by calling the addVAT method and multiplying it by the desired quantity = totalCost will then be displayed on screen for the customer after a calculate button is clicked.
Shopping basket and calculations |  | As a customer I want to be able to add my selected items to a basket so that I can keep track of what my order is. | 11 | 1 | Sprint 2 | A button that will add the item and quantity of the item to a read only text area (basket) and will then clear the selected items so that the customer can add more items to the basket. This text area will display the the items sleected, the quantity of those items and the total cost of all the items added together.
Change calculator |  | As a customer I need to be able to input | 12 | 5 | Sprint 2
| 2 |  | 13 | 5 | Sprint 3
| 3 |  | 14 | 2 | Sprint 3
| 7 |  | 15 | 2 | Sprint 3
| 10 |  | 16 | 2 | Sprint 3
| 13 |  | 17 | 2 | Sprint 3
|  | Team Capacity | 18 hours
|  | Total Points |  | 47

## Sprint 1 Backlog
User Story No. | Story Points | Task No. | Task Detail | Owner | Status | Hours remaining | Actual Time taken
1 | 1 | 1 | home screen with buttons to 4 other screens and 3 pictures of the team. The 4 buttons should bring you to the customer page, suppliers page, stock page, and orders page. | Victor | in progress
4 | 2 | 2 | Create an array to hold customer records. customerNo, name, address, telephone, gender and industry. Each variable will need a textfield to take in the details of the customer. |  | to do
11 | 3 | 3 | Create an array to hold products. productID , name, Description, price, quantity. Each variable will need a textfield to intake the products detail. |  | to do
8 | 3 | 4 | Create an array to hold supliers. supplierNo, name, address, telephone, productSupplied. Each variable will need a textfield to intake the supplier details |  | to do
15 | 5 | 5 | In the stock page there should be a drop down menu displaying the products. To add products the product should be selected and quantity required input throught a textfield. The stock amount of that product will than be updated |  | to do
14 | 2 | 6 | If statement to check wether quantity of any given item is below 5. A method in product class to do the check |  | to do

## Sprint 2 Backlog
User Story No. | Story Points | Task No. | Task Detail | Owner | Status | Hours remaining | Actual Time taken
16 | 3 | 7 |  |  | to do
5 | 3 | 8 |  |  | to do
9 | 3 | 9 |  |  | to do
12 | 3 | 10 |  |  | to do
17 | 1 | 11 |  |  | to do
6 | 5 | 12 |  |  | to do

## Sprint 3 Backlog
User Story No. | Story Points | Task No. | Task detail | Owner | Status | Hours remaining | Actual Time taken
2 | 5 | 13 |  |  | to do
3 | 2 | 14 |  |  | to do
7 | 2 | 15 |  |  | to do
10 | 2 | 16 |  |  | to do
13 | 2 | 17 |  |  | to do

## Sheet2
0 | Sprint 1 | To do
1 | Sprint 2 | In progress
2 | Sprint 3 | Done
3
5
8
13